## ship
Ship_Name | Ship_Index | Ship_Type | Category | Launching_Date | Delivery_Date | Operation_Name | Operation_Index | Operation_Type | Order | Start_Date | Finish_Date | Duration | Interruption | Fixed_Duration
J-1 | 0 | LNG | 8 | 0 | 231 | O-1-1 | 0 | 화물창 | 1 | 0 | 76 | 76 | N | 0
J-1 | 0 | LNG | 8 | 0 | 231 | O-1-2 | 1 | P/T | 2 | 76 | 96 | 20 | F | 15
J-1 | 0 | LNG | 8 | 0 | 231 | O-1-3 | 2 | 화물창족철 | 3 | 96 | 128 | 32 | N | 0
J-1 | 0 | LNG | 8 | 0 | 231 | O-1-4 | 3 | 화물창메공 | 4 | 128 | 162 | 34 | F | 26
J-1 | 0 | LNG | 8 | 0 | 231 | O-1-5 | 4 | 시운전 | 5 | 162 | 175 | 13 | N | 0
J-1 | 0 | LNG | 8 | 0 | 231 | O-1-6 | 5 | C/T | 6 | 175 | 188 | 13 | S | 7
J-1 | 0 | LNG | 8 | 0 | 231 | O-1-7 | 6 | G/T | 7 | 188 | 208 | 20 | N | 0
J-1 | 0 | LNG | 8 | 0 | 231 | O-1-8 | 7 | 인도준비 | 8 | 208 | 231 | 23 | S | 5
J-2 | 1 | PC | 7 | 0 | 118 | O-2-1 | 8 | 특수도장 | 1 | 0 | 38 | 38 | N | 0
J-2 | 1 | PC | 7 | 0 | 118 | O-2-2 | 9 | 화물창 | 2 | 38 | 78 | 40 | N | 0
J-2 | 1 | PC | 7 | 0 | 118 | O-2-3 | 10 | 시운전 | 3 | 78 | 90 | 12 | N | 0
J-2 | 1 | PC | 7 | 0 | 118 | O-2-4 | 11 | 인도준비 | 4 | 90 | 118 | 28 | S | 15
J-3 | 2 | VL_CONT | 6 | 2 | 133 | O-3-1 | 12 | 축계작업 | 1 | 2 | 93 | 91 | F | 15
J-3 | 2 | VL_CONT | 6 | 2 | 133 | O-3-2 | 13 | 시운전 | 2 | 93 | 106 | 13 | N | 0
J-3 | 2 | VL_CONT | 6 | 2 | 133 | O-3-3 | 14 | 인도준비 | 3 | 106 | 133 | 27 | N | 0
J-4 | 3 | LNG | 8 | 2 | 223 | O-4-1 | 15 | 화물창 | 1 | 2 | 74 | 72 | N | 0
J-4 | 3 | LNG | 8 | 2 | 223 | O-4-2 | 16 | P/T | 2 | 74 | 93 | 19 | F | 15
J-4 | 3 | LNG | 8 | 2 | 223 | O-4-3 | 17 | 화물창족철 | 3 | 93 | 123 | 30 | N | 0
J-4 | 3 | LNG | 8 | 2 | 223 | O-4-4 | 18 | 화물창메공 | 4 | 123 | 156 | 33 | F | 26
J-4 | 3 | LNG | 8 | 2 | 223 | O-4-5 | 19 | 시운전 | 5 | 156 | 169 | 13 | N | 0
J-4 | 3 | LNG | 8 | 2 | 223 | O-4-6 | 20 | C/T | 6 | 169 | 182 | 13 | S | 7
J-4 | 3 | LNG | 8 | 2 | 223 | O-4-7 | 21 | G/T | 7 | 182 | 201 | 19 | N | 0
J-4 | 3 | LNG | 8 | 2 | 223 | O-4-8 | 22 | 인도준비 | 8 | 201 | 223 | 22 | S | 5
J-5 | 4 | VL_CONT | 6 | 5 | 145 | O-5-1 | 23 | 축계작업 | 1 | 5 | 103 | 98 | F | 15
J-5 | 4 | VL_CONT | 6 | 5 | 145 | O-5-2 | 24 | 시운전 | 2 | 103 | 117 | 14 | N | 0
J-5 | 4 | VL_CONT | 6 | 5 | 145 | O-5-3 | 25 | 인도준비 | 3 | 117 | 145 | 28 | N | 0
J-6 | 5 | L_CONT | 5 | 12 | 95 | O-6-1 | 26 | 축계작업 | 1 | 12 | 70 | 58 | F | 15
J-6 | 5 | L_CONT | 5 | 12 | 95 | O-6-2 | 27 | 시운전 | 2 | 70 | 78 | 8 | N | 0
J-6 | 5 | L_CONT | 5 | 12 | 95 | O-6-3 | 28 | 인도준비 | 3 | 78 | 95 | 17 | N | 0
J-7 | 6 | L_CONT | 5 | 18 | 108 | O-7-1 | 29 | 축계작업 | 1 | 18 | 80 | 62 | F | 15
J-7 | 6 | L_CONT | 5 | 18 | 108 | O-7-2 | 30 | 시운전 | 2 | 80 | 89 | 9 | N | 0
J-7 | 6 | L_CONT | 5 | 18 | 108 | O-7-3 | 31 | 인도준비 | 3 | 89 | 108 | 19 | N | 0
J-8 | 7 | PC | 7 | 19 | 148 | O-8-1 | 32 | 특수도장 | 1 | 19 | 61 | 42 | N | 0
J-8 | 7 | PC | 7 | 19 | 148 | O-8-2 | 33 | 화물창 | 2 | 61 | 104 | 43 | N | 0
J-8 | 7 | PC | 7 | 19 | 148 | O-8-3 | 34 | 시운전 | 3 | 104 | 118 | 14 | N | 0
J-8 | 7 | PC | 7 | 19 | 148 | O-8-4 | 35 | 인도준비 | 4 | 118 | 148 | 30 | S | 15
J-9 | 8 | LNG | 8 | 20 | 311 | O-9-1 | 36 | 화물창 | 1 | 20 | 116 | 96 | N | 0
J-9 | 8 | LNG | 8 | 20 | 311 | O-9-2 | 37 | P/T | 2 | 116 | 142 | 26 | F | 15
J-9 | 8 | LNG | 8 | 20 | 311 | O-9-3 | 38 | 화물창족철 | 3 | 142 | 182 | 40 | N | 0
J-9 | 8 | LNG | 8 | 20 | 311 | O-9-4 | 39 | 화물창메공 | 4 | 182 | 225 | 43 | F | 26
J-9 | 8 | LNG | 8 | 20 | 311 | O-9-5 | 40 | 시운전 | 5 | 225 | 242 | 17 | N | 0
J-9 | 8 | LNG | 8 | 20 | 311 | O-9-6 | 41 | C/T | 6 | 242 | 259 | 17 | S | 7
J-9 | 8 | LNG | 8 | 20 | 311 | O-9-7 | 42 | G/T | 7 | 259 | 285 | 26 | N | 0
J-9 | 8 | LNG | 8 | 20 | 311 | O-9-8 | 43 | 인도준비 | 8 | 285 | 311 | 26 | S | 5
J-10 | 9 | VL_CONT | 6 | 20 | 144 | O-10-1 | 44 | 축계작업 | 1 | 20 | 106 | 86 | F | 15
J-10 | 9 | VL_CONT | 6 | 20 | 144 | O-10-2 | 45 | 시운전 | 2 | 106 | 118 | 12 | N | 0
J-10 | 9 | VL_CONT | 6 | 20 | 144 | O-10-3 | 46 | 인도준비 | 3 | 118 | 144 | 26 | N | 0
J-11 | 10 | VL_CONT | 6 | 22 | 160 | O-11-1 | 47 | 축계작업 | 1 | 22 | 118 | 96 | F | 15
J-11 | 10 | VL_CONT | 6 | 22 | 160 | O-11-2 | 48 | 시운전 | 2 | 118 | 131 | 13 | N | 0
J-11 | 10 | VL_CONT | 6 | 22 | 160 | O-11-3 | 49 | 인도준비 | 3 | 131 | 160 | 29 | N | 0
J-12 | 11 | VL_CONT | 6 | 22 | 141 | O-12-1 | 50 | 축계작업 | 1 | 22 | 105 | 83 | F | 15
J-12 | 11 | VL_CONT | 6 | 22 | 141 | O-12-2 | 51 | 시운전 | 2 | 105 | 116 | 11 | N | 0
J-12 | 11 | VL_CONT | 6 | 22 | 141 | O-12-3 | 52 | 인도준비 | 3 | 116 | 141 | 25 | N | 0
J-13 | 12 | LNG | 8 | 24 | 344 | O-13-1 | 53 | 화물창 | 1 | 24 | 129 | 105 | N | 0
J-13 | 12 | LNG | 8 | 24 | 344 | O-13-2 | 54 | P/T | 2 | 129 | 157 | 28 | F | 15
J-13 | 12 | LNG | 8 | 24 | 344 | O-13-3 | 55 | 화물창족철 | 3 | 157 | 201 | 44 | N | 0
J-13 | 12 | LNG | 8 | 24 | 344 | O-13-4 | 56 | 화물창메공 | 4 | 201 | 249 | 48 | F | 26
J-13 | 12 | LNG | 8 | 24 | 344 | O-13-5 | 57 | 시운전 | 5 | 249 | 268 | 19 | N | 0
J-13 | 12 | LNG | 8 | 24 | 344 | O-13-6 | 58 | C/T | 6 | 268 | 287 | 19 | S | 7
J-13 | 12 | LNG | 8 | 24 | 344 | O-13-7 | 59 | G/T | 7 | 287 | 315 | 28 | N | 0
J-13 | 12 | LNG | 8 | 24 | 344 | O-13-8 | 60 | 인도준비 | 8 | 315 | 344 | 29 | S | 5
J-14 | 13 | A_COT | 4 | 27 | 128 | O-14-1 | 61 | 축계작업 | 1 | 27 | 80 | 53 | F | 10
J-14 | 13 | A_COT | 4 | 27 | 128 | O-14-2 | 62 | 시운전 | 2 | 80 | 99 | 19 | N | 0
J-14 | 13 | A_COT | 4 | 27 | 128 | O-14-3 | 63 | 인도준비 | 3 | 99 | 128 | 29 | N | 0
J-15 | 14 | LNG | 8 | 27 | 348 | O-15-1 | 64 | 화물창 | 1 | 27 | 132 | 105 | N | 0
J-15 | 14 | LNG | 8 | 27 | 348 | O-15-2 | 65 | P/T | 2 | 132 | 160 | 28 | F | 15
J-15 | 14 | LNG | 8 | 27 | 348 | O-15-3 | 66 | 화물창족철 | 3 | 160 | 204 | 44 | N | 0
J-15 | 14 | LNG | 8 | 27 | 348 | O-15-4 | 67 | 화물창메공 | 4 | 204 | 252 | 48 | F | 26
J-15 | 14 | LNG | 8 | 27 | 348 | O-15-5 | 68 | 시운전 | 5 | 252 | 271 | 19 | N | 0
J-15 | 14 | LNG | 8 | 27 | 348 | O-15-6 | 69 | C/T | 6 | 271 | 290 | 19 | S | 7
J-15 | 14 | LNG | 8 | 27 | 348 | O-15-7 | 70 | G/T | 7 | 290 | 318 | 28 | N | 0
J-15 | 14 | LNG | 8 | 27 | 348 | O-15-8 | 71 | 인도준비 | 8 | 318 | 348 | 30 | S | 5
J-16 | 15 | LNG | 8 | 34 | 307 | O-16-1 | 72 | 화물창 | 1 | 34 | 124 | 90 | N | 0
J-16 | 15 | LNG | 8 | 34 | 307 | O-16-2 | 73 | P/T | 2 | 124 | 148 | 24 | F | 15
J-16 | 15 | LNG | 8 | 34 | 307 | O-16-3 | 74 | 화물창족철 | 3 | 148 | 186 | 38 | N | 0
J-16 | 15 | LNG | 8 | 34 | 307 | O-16-4 | 75 | 화물창메공 | 4 | 186 | 226 | 40 | F | 26
J-16 | 15 | LNG | 8 | 34 | 307 | O-16-5 | 76 | 시운전 | 5 | 226 | 242 | 16 | N | 0
J-16 | 15 | LNG | 8 | 34 | 307 | O-16-6 | 77 | C/T | 6 | 242 | 258 | 16 | S | 7
J-16 | 15 | LNG | 8 | 34 | 307 | O-16-7 | 78 | G/T | 7 | 258 | 282 | 24 | N | 0
J-16 | 15 | LNG | 8 | 34 | 307 | O-16-8 | 79 | 인도준비 | 8 | 282 | 307 | 25 | S | 5
J-17 | 16 | A_COT | 4 | 37 | 123 | O-17-1 | 80 | 축계작업 | 1 | 37 | 82 | 45 | F | 10
J-17 | 16 | A_COT | 4 | 37 | 123 | O-17-2 | 81 | 시운전 | 2 | 82 | 98 | 16 | N | 0
J-17 | 16 | A_COT | 4 | 37 | 123 | O-17-3 | 82 | 인도준비 | 3 | 98 | 123 | 25 | N | 0
J-18 | 17 | S_SHTL | 1 | 40 | 160 | O-18-1 | 83 | 축계작업 | 1 | 40 | 128 | 88 | F | 15
J-18 | 17 | S_SHTL | 1 | 40 | 160 | O-18-2 | 84 | 시운전 | 2 | 128 | 141 | 13 | N | 0
J-18 | 17 | S_SHTL | 1 | 40 | 160 | O-18-3 | 85 | 인도준비 | 3 | 141 | 160 | 19 | N | 0
J-19 | 18 | A_SHTL | 2 | 47 | 310 | O-19-1 | 86 | 축계작업 | 1 | 47 | 241 | 194 | F | 15
J-19 | 18 | A_SHTL | 2 | 47 | 310 | O-19-2 | 87 | 시운전 | 2 | 241 | 269 | 28 | N | 0
J-19 | 18 | A_SHTL | 2 | 47 | 310 | O-19-3 | 88 | 인도준비 | 3 | 269 | 310 | 41 | N | 0
J-20 | 19 | S_SHTL | 1 | 47 | 173 | O-20-1 | 89 | 축계작업 | 1 | 47 | 140 | 93 | F | 15
J-20 | 19 | S_SHTL | 1 | 47 | 173 | O-20-2 | 90 | 시운전 | 2 | 140 | 153 | 13 | N | 0
J-20 | 19 | S_SHTL | 1 | 47 | 173 | O-20-3 | 91 | 인도준비 | 3 | 153 | 173 | 20 | N | 0
J-21 | 20 | VL_CONT | 6 | 50 | 192 | O-21-1 | 92 | 축계작업 | 1 | 50 | 149 | 99 | F | 15
J-21 | 20 | VL_CONT | 6 | 50 | 192 | O-21-2 | 93 | 시운전 | 2 | 149 | 163 | 14 | N | 0
J-21 | 20 | VL_CONT | 6 | 50 | 192 | O-21-3 | 94 | 인도준비 | 3 | 163 | 192 | 29 | N | 0
J-22 | 21 | S_SHTL | 1 | 56 | 309 | O-22-1 | 95 | 축계작업 | 1 | 56 | 243 | 187 | F | 15
J-22 | 21 | S_SHTL | 1 | 56 | 309 | O-22-2 | 96 | 시운전 | 2 | 243 | 270 | 27 | N | 0
J-22 | 21 | S_SHTL | 1 | 56 | 309 | O-22-3 | 97 | 인도준비 | 3 | 270 | 309 | 39 | N | 0
J-23 | 22 | S_COT | 3 | 64 | 161 | O-23-1 | 98 | 축계작업 | 1 | 64 | 115 | 51 | F | 10
J-23 | 22 | S_COT | 3 | 64 | 161 | O-23-2 | 99 | 시운전 | 2 | 115 | 133 | 18 | N | 0
J-23 | 22 | S_COT | 3 | 64 | 161 | O-23-3 | 100 | 인도준비 | 3 | 133 | 161 | 28 | N | 0
J-24 | 23 | LNG | 8 | 65 | 349 | O-24-1 | 101 | 화물창 | 1 | 65 | 158 | 93 | N | 0
J-24 | 23 | LNG | 8 | 65 | 349 | O-24-2 | 102 | P/T | 2 | 158 | 183 | 25 | F | 15
J-24 | 23 | LNG | 8 | 65 | 349 | O-24-3 | 103 | 화물창족철 | 3 | 183 | 222 | 39 | N | 0
J-24 | 23 | LNG | 8 | 65 | 349 | O-24-4 | 104 | 화물창메공 | 4 | 222 | 264 | 42 | F | 26
J-24 | 23 | LNG | 8 | 65 | 349 | O-24-5 | 105 | 시운전 | 5 | 264 | 281 | 17 | N | 0
J-24 | 23 | LNG | 8 | 65 | 349 | O-24-6 | 106 | C/T | 6 | 281 | 298 | 17 | S | 7
J-24 | 23 | LNG | 8 | 65 | 349 | O-24-7 | 107 | G/T | 7 | 298 | 323 | 25 | N | 0
J-24 | 23 | LNG | 8 | 65 | 349 | O-24-8 | 108 | 인도준비 | 8 | 323 | 349 | 26 | S | 5
J-25 | 24 | LNG | 8 | 81 | 298 | O-25-1 | 109 | 화물창 | 1 | 81 | 152 | 71 | N | 0
J-25 | 24 | LNG | 8 | 81 | 298 | O-25-2 | 110 | P/T | 2 | 152 | 171 | 19 | F | 15
J-25 | 24 | LNG | 8 | 81 | 298 | O-25-3 | 111 | 화물창족철 | 3 | 171 | 201 | 30 | N | 0
J-25 | 24 | LNG | 8 | 81 | 298 | O-25-4 | 112 | 화물창메공 | 4 | 201 | 233 | 32 | F | 26
J-25 | 24 | LNG | 8 | 81 | 298 | O-25-5 | 113 | 시운전 | 5 | 233 | 246 | 13 | N | 0
J-25 | 24 | LNG | 8 | 81 | 298 | O-25-6 | 114 | C/T | 6 | 246 | 259 | 13 | S | 7
J-25 | 24 | LNG | 8 | 81 | 298 | O-25-7 | 115 | G/T | 7 | 259 | 278 | 19 | N | 0
J-25 | 24 | LNG | 8 | 81 | 298 | O-25-8 | 116 | 인도준비 | 8 | 278 | 298 | 20 | S | 5
J-26 | 25 | LNG | 8 | 81 | 338 | O-26-1 | 117 | 화물창 | 1 | 81 | 165 | 84 | N | 0
J-26 | 25 | LNG | 8 | 81 | 338 | O-26-2 | 118 | P/T | 2 | 165 | 188 | 23 | F | 15
J-26 | 25 | LNG | 8 | 81 | 338 | O-26-3 | 119 | 화물창족철 | 3 | 188 | 223 | 35 | N | 0
J-26 | 25 | LNG | 8 | 81 | 338 | O-26-4 | 120 | 화물창메공 | 4 | 223 | 261 | 38 | F | 26
J-26 | 25 | LNG | 8 | 81 | 338 | O-26-5 | 121 | 시운전 | 5 | 261 | 276 | 15 | N | 0
J-26 | 25 | LNG | 8 | 81 | 338 | O-26-6 | 122 | C/T | 6 | 276 | 291 | 15 | S | 7
J-26 | 25 | LNG | 8 | 81 | 338 | O-26-7 | 123 | G/T | 7 | 291 | 314 | 23 | N | 0
J-26 | 25 | LNG | 8 | 81 | 338 | O-26-8 | 124 | 인도준비 | 8 | 314 | 338 | 24 | S | 5
J-27 | 26 | VL_CONT | 6 | 84 | 195 | O-27-1 | 125 | 축계작업 | 1 | 84 | 161 | 77 | F | 15
J-27 | 26 | VL_CONT | 6 | 84 | 195 | O-27-2 | 126 | 시운전 | 2 | 161 | 172 | 11 | N | 0
J-27 | 26 | VL_CONT | 6 | 84 | 195 | O-27-3 | 127 | 인도준비 | 3 | 172 | 195 | 23 | N | 0
J-28 | 27 | S_SHTL | 1 | 86 | 292 | O-28-1 | 128 | 축계작업 | 1 | 86 | 238 | 152 | F | 15
J-28 | 27 | S_SHTL | 1 | 86 | 292 | O-28-2 | 129 | 시운전 | 2 | 238 | 260 | 22 | N | 0
J-28 | 27 | S_SHTL | 1 | 86 | 292 | O-28-3 | 130 | 인도준비 | 3 | 260 | 292 | 32 | N | 0
J-29 | 28 | L_CONT | 5 | 88 | 164 | O-29-1 | 131 | 축계작업 | 1 | 88 | 141 | 53 | F | 15
J-29 | 28 | L_CONT | 5 | 88 | 164 | O-29-2 | 132 | 시운전 | 2 | 141 | 148 | 7 | N | 0
J-29 | 28 | L_CONT | 5 | 88 | 164 | O-29-3 | 133 | 인도준비 | 3 | 148 | 164 | 16 | N | 0
J-30 | 29 | S_COT | 3 | 92 | 225 | O-30-1 | 134 | 축계작업 | 1 | 92 | 162 | 70 | F | 10
J-30 | 29 | S_COT | 3 | 92 | 225 | O-30-2 | 135 | 시운전 | 2 | 162 | 187 | 25 | N | 0
J-30 | 29 | S_COT | 3 | 92 | 225 | O-30-3 | 136 | 인도준비 | 3 | 187 | 225 | 38 | N | 0
J-31 | 30 | LNG | 8 | 92 | 280 | O-31-1 | 137 | 화물창 | 1 | 92 | 154 | 62 | N | 0
J-31 | 30 | LNG | 8 | 92 | 280 | O-31-2 | 138 | P/T | 2 | 154 | 170 | 16 | F | 15
J-31 | 30 | LNG | 8 | 92 | 280 | O-31-3 | 139 | 화물창족철 | 3 | 170 | 196 | 26 | N | 0
J-31 | 30 | LNG | 8 | 92 | 280 | O-31-4 | 140 | 화물창메공 | 4 | 196 | 224 | 28 | F | 26
J-31 | 30 | LNG | 8 | 92 | 280 | O-31-5 | 141 | 시운전 | 5 | 224 | 235 | 11 | N | 0
J-31 | 30 | LNG | 8 | 92 | 280 | O-31-6 | 142 | C/T | 6 | 235 | 246 | 11 | S | 7
J-31 | 30 | LNG | 8 | 92 | 280 | O-31-7 | 143 | G/T | 7 | 246 | 262 | 16 | N | 0
J-31 | 30 | LNG | 8 | 92 | 280 | O-31-8 | 144 | 인도준비 | 8 | 262 | 280 | 18 | S | 5
J-32 | 31 | A_SHTL | 2 | 92 | 269 | O-32-1 | 145 | 축계작업 | 1 | 92 | 222 | 130 | F | 15
J-32 | 31 | A_SHTL | 2 | 92 | 269 | O-32-2 | 146 | 시운전 | 2 | 222 | 241 | 19 | N | 0
J-32 | 31 | A_SHTL | 2 | 92 | 269 | O-32-3 | 147 | 인도준비 | 3 | 241 | 269 | 28 | N | 0
J-33 | 32 | S_SHTL | 1 | 98 | 352 | O-33-1 | 148 | 축계작업 | 1 | 98 | 285 | 187 | F | 15
J-33 | 32 | S_SHTL | 1 | 98 | 352 | O-33-2 | 149 | 시운전 | 2 | 285 | 312 | 27 | N | 0
J-33 | 32 | S_SHTL | 1 | 98 | 352 | O-33-3 | 150 | 인도준비 | 3 | 312 | 352 | 40 | N | 0
J-34 | 33 | S_SHTL | 1 | 98 | 304 | O-34-1 | 151 | 축계작업 | 1 | 98 | 250 | 152 | F | 15
J-34 | 33 | S_SHTL | 1 | 98 | 304 | O-34-2 | 152 | 시운전 | 2 | 250 | 272 | 22 | N | 0
J-34 | 33 | S_SHTL | 1 | 98 | 304 | O-34-3 | 153 | 인도준비 | 3 | 272 | 304 | 32 | N | 0
J-35 | 34 | LNG | 8 | 99 | 327 | O-35-1 | 154 | 화물창 | 1 | 99 | 174 | 75 | N | 0
J-35 | 34 | LNG | 8 | 99 | 327 | O-35-2 | 155 | P/T | 2 | 174 | 194 | 20 | F | 15
J-35 | 34 | LNG | 8 | 99 | 327 | O-35-3 | 156 | 화물창족철 | 3 | 194 | 225 | 31 | N | 0
J-35 | 34 | LNG | 8 | 99 | 327 | O-35-4 | 157 | 화물창메공 | 4 | 225 | 259 | 34 | F | 26
J-35 | 34 | LNG | 8 | 99 | 327 | O-35-5 | 158 | 시운전 | 5 | 259 | 272 | 13 | N | 0
J-35 | 34 | LNG | 8 | 99 | 327 | O-35-6 | 159 | C/T | 6 | 272 | 285 | 13 | S | 7
J-35 | 34 | LNG | 8 | 99 | 327 | O-35-7 | 160 | G/T | 7 | 285 | 305 | 20 | N | 0
J-35 | 34 | LNG | 8 | 99 | 327 | O-35-8 | 161 | 인도준비 | 8 | 305 | 327 | 22 | S | 5
J-36 | 35 | S_SHTL | 1 | 99 | 419 | O-36-1 | 162 | 축계작업 | 1 | 99 | 335 | 236 | F | 15
J-36 | 35 | S_SHTL | 1 | 99 | 419 | O-36-2 | 163 | 시운전 | 2 | 335 | 370 | 35 | N | 0
J-36 | 35 | S_SHTL | 1 | 99 | 419 | O-36-3 | 164 | 인도준비 | 3 | 370 | 419 | 49 | N | 0
J-37 | 36 | LNG | 8 | 106 | 304 | O-37-1 | 165 | 화물창 | 1 | 106 | 171 | 65 | N | 0
J-37 | 36 | LNG | 8 | 106 | 304 | O-37-2 | 166 | P/T | 2 | 171 | 188 | 17 | F | 15
J-37 | 36 | LNG | 8 | 106 | 304 | O-37-3 | 167 | 화물창족철 | 3 | 188 | 215 | 27 | N | 0
J-37 | 36 | LNG | 8 | 106 | 304 | O-37-4 | 168 | 화물창메공 | 4 | 215 | 244 | 29 | F | 26
J-37 | 36 | LNG | 8 | 106 | 304 | O-37-5 | 169 | 시운전 | 5 | 244 | 255 | 11 | N | 0
J-37 | 36 | LNG | 8 | 106 | 304 | O-37-6 | 170 | C/T | 6 | 255 | 266 | 11 | S | 7
J-37 | 36 | LNG | 8 | 106 | 304 | O-37-7 | 171 | G/T | 7 | 266 | 283 | 17 | N | 0
J-37 | 36 | LNG | 8 | 106 | 304 | O-37-8 | 172 | 인도준비 | 8 | 283 | 304 | 21 | S | 5
J-38 | 37 | LNG | 8 | 121 | 345 | O-38-1 | 173 | 화물창 | 1 | 121 | 194 | 73 | N | 0
J-38 | 37 | LNG | 8 | 121 | 345 | O-38-2 | 174 | P/T | 2 | 194 | 214 | 20 | F | 15
J-38 | 37 | LNG | 8 | 121 | 345 | O-38-3 | 175 | 화물창족철 | 3 | 214 | 245 | 31 | N | 0
J-38 | 37 | LNG | 8 | 121 | 345 | O-38-4 | 176 | 화물창메공 | 4 | 245 | 278 | 33 | F | 26
J-38 | 37 | LNG | 8 | 121 | 345 | O-38-5 | 177 | 시운전 | 5 | 278 | 291 | 13 | N | 0
J-38 | 37 | LNG | 8 | 121 | 345 | O-38-6 | 178 | C/T | 6 | 291 | 304 | 13 | S | 7
J-38 | 37 | LNG | 8 | 121 | 345 | O-38-7 | 179 | G/T | 7 | 304 | 324 | 20 | N | 0
J-38 | 37 | LNG | 8 | 121 | 345 | O-38-8 | 180 | 인도준비 | 8 | 324 | 345 | 21 | S | 5
J-39 | 38 | LNG | 8 | 121 | 307 | O-39-1 | 181 | 화물창 | 1 | 121 | 182 | 61 | N | 0
J-39 | 38 | LNG | 8 | 121 | 307 | O-39-2 | 182 | P/T | 2 | 182 | 198 | 16 | F | 15
J-39 | 38 | LNG | 8 | 121 | 307 | O-39-3 | 183 | 화물창족철 | 3 | 198 | 224 | 26 | N | 0
J-39 | 38 | LNG | 8 | 121 | 307 | O-39-4 | 184 | 화물창메공 | 4 | 224 | 251 | 27 | F | 26
J-39 | 38 | LNG | 8 | 121 | 307 | O-39-5 | 185 | 시운전 | 5 | 251 | 262 | 11 | N | 0
J-39 | 38 | LNG | 8 | 121 | 307 | O-39-6 | 186 | C/T | 6 | 262 | 273 | 11 | S | 7
J-39 | 38 | LNG | 8 | 121 | 307 | O-39-7 | 187 | G/T | 7 | 273 | 289 | 16 | N | 0
J-39 | 38 | LNG | 8 | 121 | 307 | O-39-8 | 188 | 인도준비 | 8 | 289 | 307 | 18 | S | 5
J-40 | 39 | S_COT | 3 | 123 | 233 | O-40-1 | 189 | 축계작업 | 1 | 123 | 181 | 58 | F | 10
J-40 | 39 | S_COT | 3 | 123 | 233 | O-40-2 | 190 | 시운전 | 2 | 181 | 201 | 20 | N | 0
J-40 | 39 | S_COT | 3 | 123 | 233 | O-40-3 | 191 | 인도준비 | 3 | 201 | 233 | 32 | N | 0
J-41 | 40 | LNG | 8 | 131 | 446 | O-41-1 | 192 | 화물창 | 1 | 131 | 234 | 103 | N | 0
J-41 | 40 | LNG | 8 | 131 | 446 | O-41-2 | 193 | P/T | 2 | 234 | 262 | 28 | F | 15
J-41 | 40 | LNG | 8 | 131 | 446 | O-41-3 | 194 | 화물창족철 | 3 | 262 | 306 | 44 | N | 0
J-41 | 40 | LNG | 8 | 131 | 446 | O-41-4 | 195 | 화물창메공 | 4 | 306 | 353 | 47 | F | 26
J-41 | 40 | LNG | 8 | 131 | 446 | O-41-5 | 196 | 시운전 | 5 | 353 | 371 | 18 | N | 0
J-41 | 40 | LNG | 8 | 131 | 446 | O-41-6 | 197 | C/T | 6 | 371 | 389 | 18 | S | 7
J-41 | 40 | LNG | 8 | 131 | 446 | O-41-7 | 198 | G/T | 7 | 389 | 417 | 28 | N | 0
J-41 | 40 | LNG | 8 | 131 | 446 | O-41-8 | 199 | 인도준비 | 8 | 417 | 446 | 29 | S | 5
J-42 | 41 | LNG | 8 | 131 | 442 | O-42-1 | 200 | 화물창 | 1 | 131 | 233 | 102 | N | 0
J-42 | 41 | LNG | 8 | 131 | 442 | O-42-2 | 201 | P/T | 2 | 233 | 260 | 27 | F | 15
J-42 | 41 | LNG | 8 | 131 | 442 | O-42-3 | 202 | 화물창족철 | 3 | 260 | 303 | 43 | N | 0
J-42 | 41 | LNG | 8 | 131 | 442 | O-42-4 | 203 | 화물창메공 | 4 | 303 | 349 | 46 | F | 26
J-42 | 41 | LNG | 8 | 131 | 442 | O-42-5 | 204 | 시운전 | 5 | 349 | 367 | 18 | N | 0
J-42 | 41 | LNG | 8 | 131 | 442 | O-42-6 | 205 | C/T | 6 | 367 | 385 | 18 | S | 7
J-42 | 41 | LNG | 8 | 131 | 442 | O-42-7 | 206 | G/T | 7 | 385 | 412 | 27 | N | 0
J-42 | 41 | LNG | 8 | 131 | 442 | O-42-8 | 207 | 인도준비 | 8 | 412 | 442 | 30 | S | 5
J-43 | 42 | S_SHTL | 1 | 143 | 464 | O-43-1 | 208 | 축계작업 | 1 | 143 | 380 | 237 | F | 15
J-43 | 42 | S_SHTL | 1 | 143 | 464 | O-43-2 | 209 | 시운전 | 2 | 380 | 415 | 35 | N | 0
J-43 | 42 | S_SHTL | 1 | 143 | 464 | O-43-3 | 210 | 인도준비 | 3 | 415 | 464 | 49 | N | 0
J-44 | 43 | LNG | 8 | 145 | 358 | O-44-1 | 211 | 화물창 | 1 | 145 | 215 | 70 | N | 0
J-44 | 43 | LNG | 8 | 145 | 358 | O-44-2 | 212 | P/T | 2 | 215 | 234 | 19 | F | 15
J-44 | 43 | LNG | 8 | 145 | 358 | O-44-3 | 213 | 화물창족철 | 3 | 234 | 263 | 29 | N | 0
J-44 | 43 | LNG | 8 | 145 | 358 | O-44-4 | 214 | 화물창메공 | 4 | 263 | 294 | 31 | F | 26
J-44 | 43 | LNG | 8 | 145 | 358 | O-44-5 | 215 | 시운전 | 5 | 294 | 306 | 12 | N | 0
J-44 | 43 | LNG | 8 | 145 | 358 | O-44-6 | 216 | C/T | 6 | 306 | 318 | 12 | S | 7
J-44 | 43 | LNG | 8 | 145 | 358 | O-44-7 | 217 | G/T | 7 | 318 | 337 | 19 | N | 0
J-44 | 43 | LNG | 8 | 145 | 358 | O-44-8 | 218 | 인도준비 | 8 | 337 | 358 | 21 | S | 5
J-45 | 44 | LNG | 8 | 145 | 366 | O-45-1 | 219 | 화물창 | 1 | 145 | 217 | 72 | N | 0
J-45 | 44 | LNG | 8 | 145 | 366 | O-45-2 | 220 | P/T | 2 | 217 | 236 | 19 | F | 15
J-45 | 44 | LNG | 8 | 145 | 366 | O-45-3 | 221 | 화물창족철 | 3 | 236 | 266 | 30 | N | 0
J-45 | 44 | LNG | 8 | 145 | 366 | O-45-4 | 222 | 화물창메공 | 4 | 266 | 299 | 33 | F | 26
J-45 | 44 | LNG | 8 | 145 | 366 | O-45-5 | 223 | 시운전 | 5 | 299 | 312 | 13 | N | 0
J-45 | 44 | LNG | 8 | 145 | 366 | O-45-6 | 224 | C/T | 6 | 312 | 325 | 13 | S | 7
J-45 | 44 | LNG | 8 | 145 | 366 | O-45-7 | 225 | G/T | 7 | 325 | 344 | 19 | N | 0
J-45 | 44 | LNG | 8 | 145 | 366 | O-45-8 | 226 | 인도준비 | 8 | 344 | 366 | 22 | S | 5
J-46 | 45 | S_COT | 3 | 159 | 266 | O-46-1 | 227 | 축계작업 | 1 | 159 | 215 | 56 | F | 10
J-46 | 45 | S_COT | 3 | 159 | 266 | O-46-2 | 228 | 시운전 | 2 | 215 | 235 | 20 | N | 0
J-46 | 45 | S_COT | 3 | 159 | 266 | O-46-3 | 229 | 인도준비 | 3 | 235 | 266 | 31 | N | 0
J-47 | 46 | S_SHTL | 1 | 162 | 430 | O-47-1 | 230 | 축계작업 | 1 | 162 | 360 | 198 | F | 15
J-47 | 46 | S_SHTL | 1 | 162 | 430 | O-47-2 | 231 | 시운전 | 2 | 360 | 389 | 29 | N | 0
J-47 | 46 | S_SHTL | 1 | 162 | 430 | O-47-3 | 232 | 인도준비 | 3 | 389 | 430 | 41 | N | 0
J-48 | 47 | S_SHTL | 1 | 188 | 305 | O-48-1 | 233 | 축계작업 | 1 | 188 | 274 | 86 | F | 15
J-48 | 47 | S_SHTL | 1 | 188 | 305 | O-48-2 | 234 | 시운전 | 2 | 274 | 286 | 12 | N | 0
J-48 | 47 | S_SHTL | 1 | 188 | 305 | O-48-3 | 235 | 인도준비 | 3 | 286 | 305 | 19 | N | 0
J-49 | 48 | S_SHTL | 1 | 196 | 313 | O-49-1 | 236 | 축계작업 | 1 | 196 | 282 | 86 | F | 15
J-49 | 48 | S_SHTL | 1 | 196 | 313 | O-49-2 | 237 | 시운전 | 2 | 282 | 294 | 12 | N | 0
J-49 | 48 | S_SHTL | 1 | 196 | 313 | O-49-3 | 238 | 인도준비 | 3 | 294 | 313 | 19 | N | 0
J-50 | 49 | VL_CONT | 6 | 197 | 332 | O-50-1 | 239 | 축계작업 | 1 | 197 | 291 | 94 | F | 15
J-50 | 49 | VL_CONT | 6 | 197 | 332 | O-50-2 | 240 | 시운전 | 2 | 291 | 304 | 13 | N | 0
J-50 | 49 | VL_CONT | 6 | 197 | 332 | O-50-3 | 241 | 인도준비 | 3 | 304 | 332 | 28 | N | 0
J-51 | 50 | A_SHTL | 2 | 219 | 472 | O-51-1 | 242 | 축계작업 | 1 | 219 | 406 | 187 | F | 15
J-51 | 50 | A_SHTL | 2 | 219 | 472 | O-51-2 | 243 | 시운전 | 2 | 406 | 433 | 27 | N | 0
J-51 | 50 | A_SHTL | 2 | 219 | 472 | O-51-3 | 244 | 인도준비 | 3 | 433 | 472 | 39 | N | 0
J-52 | 51 | L_CONT | 5 | 220 | 292 | O-52-1 | 245 | 축계작업 | 1 | 220 | 270 | 50 | F | 15
J-52 | 51 | L_CONT | 5 | 220 | 292 | O-52-2 | 246 | 시운전 | 2 | 270 | 277 | 7 | N | 0
J-52 | 51 | L_CONT | 5 | 220 | 292 | O-52-3 | 247 | 인도준비 | 3 | 277 | 292 | 15 | N | 0
J-53 | 52 | S_SHTL | 1 | 224 | 384 | O-53-1 | 248 | 축계작업 | 1 | 224 | 342 | 118 | F | 15
J-53 | 52 | S_SHTL | 1 | 224 | 384 | O-53-2 | 249 | 시운전 | 2 | 342 | 359 | 17 | N | 0
J-53 | 52 | S_SHTL | 1 | 224 | 384 | O-53-3 | 250 | 인도준비 | 3 | 359 | 384 | 25 | N | 0
J-54 | 53 | LNG | 8 | 226 | 420 | O-54-1 | 251 | 화물창 | 1 | 226 | 290 | 64 | N | 0
J-54 | 53 | LNG | 8 | 226 | 420 | O-54-2 | 252 | P/T | 2 | 290 | 307 | 17 | F | 15
J-54 | 53 | LNG | 8 | 226 | 420 | O-54-3 | 253 | 화물창족철 | 3 | 307 | 334 | 27 | N | 0
J-54 | 53 | LNG | 8 | 226 | 420 | O-54-4 | 254 | 화물창메공 | 4 | 334 | 363 | 29 | F | 26
J-54 | 53 | LNG | 8 | 226 | 420 | O-54-5 | 255 | 시운전 | 5 | 363 | 374 | 11 | N | 0
J-54 | 53 | LNG | 8 | 226 | 420 | O-54-6 | 256 | C/T | 6 | 374 | 385 | 11 | S | 7
J-54 | 53 | LNG | 8 | 226 | 420 | O-54-7 | 257 | G/T | 7 | 385 | 402 | 17 | N | 0
J-54 | 53 | LNG | 8 | 226 | 420 | O-54-8 | 258 | 인도준비 | 8 | 402 | 420 | 18 | S | 5
J-55 | 54 | LNG | 8 | 251 | 547 | O-55-1 | 259 | 화물창 | 1 | 251 | 348 | 97 | N | 0
J-55 | 54 | LNG | 8 | 251 | 547 | O-55-2 | 260 | P/T | 2 | 348 | 374 | 26 | F | 15
J-55 | 54 | LNG | 8 | 251 | 547 | O-55-3 | 261 | 화물창족철 | 3 | 374 | 415 | 41 | N | 0
J-55 | 54 | LNG | 8 | 251 | 547 | O-55-4 | 262 | 화물창메공 | 4 | 415 | 459 | 44 | F | 26
J-55 | 54 | LNG | 8 | 251 | 547 | O-55-5 | 263 | 시운전 | 5 | 459 | 476 | 17 | N | 0
J-55 | 54 | LNG | 8 | 251 | 547 | O-55-6 | 264 | C/T | 6 | 476 | 493 | 17 | S | 7
J-55 | 54 | LNG | 8 | 251 | 547 | O-55-7 | 265 | G/T | 7 | 493 | 519 | 26 | N | 0
J-55 | 54 | LNG | 8 | 251 | 547 | O-55-8 | 266 | 인도준비 | 8 | 519 | 547 | 28 | S | 5
J-56 | 55 | VL_CONT | 6 | 254 | 366 | O-56-1 | 267 | 축계작업 | 1 | 254 | 332 | 78 | F | 15
J-56 | 55 | VL_CONT | 6 | 254 | 366 | O-56-2 | 268 | 시운전 | 2 | 332 | 343 | 11 | N | 0
J-56 | 55 | VL_CONT | 6 | 254 | 366 | O-56-3 | 269 | 인도준비 | 3 | 343 | 366 | 23 | N | 0
J-57 | 56 | VL_CONT | 6 | 254 | 358 | O-57-1 | 270 | 축계작업 | 1 | 254 | 326 | 72 | F | 15
J-57 | 56 | VL_CONT | 6 | 254 | 358 | O-57-2 | 271 | 시운전 | 2 | 326 | 336 | 10 | N | 0
J-57 | 56 | VL_CONT | 6 | 254 | 358 | O-57-3 | 272 | 인도준비 | 3 | 336 | 358 | 22 | N | 0
J-58 | 57 | S_SHTL | 1 | 254 | 472 | O-58-1 | 273 | 축계작업 | 1 | 254 | 415 | 161 | F | 15
J-58 | 57 | S_SHTL | 1 | 254 | 472 | O-58-2 | 274 | 시운전 | 2 | 415 | 438 | 23 | N | 0
J-58 | 57 | S_SHTL | 1 | 254 | 472 | O-58-3 | 275 | 인도준비 | 3 | 438 | 472 | 34 | N | 0
J-59 | 58 | VL_CONT | 6 | 260 | 383 | O-59-1 | 276 | 축계작업 | 1 | 260 | 346 | 86 | F | 15
J-59 | 58 | VL_CONT | 6 | 260 | 383 | O-59-2 | 277 | 시운전 | 2 | 346 | 358 | 12 | N | 0
J-59 | 58 | VL_CONT | 6 | 260 | 383 | O-59-3 | 278 | 인도준비 | 3 | 358 | 383 | 25 | N | 0
J-60 | 59 | PC | 7 | 261 | 389 | O-60-1 | 279 | 특수도장 | 1 | 261 | 303 | 42 | N | 0
J-60 | 59 | PC | 7 | 261 | 389 | O-60-2 | 280 | 화물창 | 2 | 303 | 346 | 43 | N | 0
J-60 | 59 | PC | 7 | 261 | 389 | O-60-3 | 281 | 시운전 | 3 | 346 | 360 | 14 | N | 0
J-60 | 59 | PC | 7 | 261 | 389 | O-60-4 | 282 | 인도준비 | 4 | 360 | 389 | 29 | S | 15
J-61 | 60 | PC | 7 | 266 | 375 | O-61-1 | 283 | 특수도장 | 1 | 266 | 301 | 35 | N | 0
J-61 | 60 | PC | 7 | 266 | 375 | O-61-2 | 284 | 화물창 | 2 | 301 | 338 | 37 | N | 0
J-61 | 60 | PC | 7 | 266 | 375 | O-61-3 | 285 | 시운전 | 3 | 338 | 349 | 11 | N | 0
J-61 | 60 | PC | 7 | 266 | 375 | O-61-4 | 286 | 인도준비 | 4 | 349 | 375 | 26 | S | 15
J-62 | 61 | S_SHTL | 1 | 269 | 438 | O-62-1 | 287 | 축계작업 | 1 | 269 | 394 | 125 | F | 15
J-62 | 61 | S_SHTL | 1 | 269 | 438 | O-62-2 | 288 | 시운전 | 2 | 394 | 412 | 18 | N | 0
J-62 | 61 | S_SHTL | 1 | 269 | 438 | O-62-3 | 289 | 인도준비 | 3 | 412 | 438 | 26 | N | 0
J-63 | 62 | S_COT | 3 | 272 | 375 | O-63-1 | 290 | 축계작업 | 1 | 272 | 326 | 54 | F | 10
J-63 | 62 | S_COT | 3 | 272 | 375 | O-63-2 | 291 | 시운전 | 2 | 326 | 345 | 19 | N | 0
J-63 | 62 | S_COT | 3 | 272 | 375 | O-63-3 | 292 | 인도준비 | 3 | 345 | 375 | 30 | N | 0
J-64 | 63 | L_CONT | 5 | 285 | 362 | O-64-1 | 293 | 축계작업 | 1 | 285 | 338 | 53 | F | 15
J-64 | 63 | L_CONT | 5 | 285 | 362 | O-64-2 | 294 | 시운전 | 2 | 338 | 345 | 7 | N | 0
J-64 | 63 | L_CONT | 5 | 285 | 362 | O-64-3 | 295 | 인도준비 | 3 | 345 | 362 | 17 | N | 0
J-65 | 64 | S_SHTL | 1 | 294 | 500 | O-65-1 | 296 | 축계작업 | 1 | 294 | 446 | 152 | F | 15
J-65 | 64 | S_SHTL | 1 | 294 | 500 | O-65-2 | 297 | 시운전 | 2 | 446 | 468 | 22 | N | 0
J-65 | 64 | S_SHTL | 1 | 294 | 500 | O-65-3 | 298 | 인도준비 | 3 | 468 | 500 | 32 | N | 0
J-66 | 65 | PC | 7 | 303 | 435 | O-66-1 | 299 | 특수도장 | 1 | 303 | 346 | 43 | N | 0
J-66 | 65 | PC | 7 | 303 | 435 | O-66-2 | 300 | 화물창 | 2 | 346 | 390 | 44 | N | 0
J-66 | 65 | PC | 7 | 303 | 435 | O-66-3 | 301 | 시운전 | 3 | 390 | 404 | 14 | N | 0
J-66 | 65 | PC | 7 | 303 | 435 | O-66-4 | 302 | 인도준비 | 4 | 404 | 435 | 31 | S | 15
J-67 | 66 | VL_CONT | 6 | 304 | 432 | O-67-1 | 303 | 축계작업 | 1 | 304 | 393 | 89 | F | 15
J-67 | 66 | VL_CONT | 6 | 304 | 432 | O-67-2 | 304 | 시운전 | 2 | 393 | 405 | 12 | N | 0
J-67 | 66 | VL_CONT | 6 | 304 | 432 | O-67-3 | 305 | 인도준비 | 3 | 405 | 432 | 27 | N | 0
J-68 | 67 | LNG | 8 | 309 | 591 | O-68-1 | 306 | 화물창 | 1 | 309 | 402 | 93 | N | 0
J-68 | 67 | LNG | 8 | 309 | 591 | O-68-2 | 307 | P/T | 2 | 402 | 427 | 25 | F | 15
J-68 | 67 | LNG | 8 | 309 | 591 | O-68-3 | 308 | 화물창족철 | 3 | 427 | 466 | 39 | N | 0
J-68 | 67 | LNG | 8 | 309 | 591 | O-68-4 | 309 | 화물창메공 | 4 | 466 | 508 | 42 | F | 26
J-68 | 67 | LNG | 8 | 309 | 591 | O-68-5 | 310 | 시운전 | 5 | 508 | 524 | 16 | N | 0
J-68 | 67 | LNG | 8 | 309 | 591 | O-68-6 | 311 | C/T | 6 | 524 | 540 | 16 | S | 7
J-68 | 67 | LNG | 8 | 309 | 591 | O-68-7 | 312 | G/T | 7 | 540 | 565 | 25 | N | 0
J-68 | 67 | LNG | 8 | 309 | 591 | O-68-8 | 313 | 인도준비 | 8 | 565 | 591 | 26 | S | 5
J-69 | 68 | LNG | 8 | 315 | 604 | O-69-1 | 314 | 화물창 | 1 | 315 | 410 | 95 | N | 0
J-69 | 68 | LNG | 8 | 315 | 604 | O-69-2 | 315 | P/T | 2 | 410 | 436 | 26 | F | 15
J-69 | 68 | LNG | 8 | 315 | 604 | O-69-3 | 316 | 화물창족철 | 3 | 436 | 476 | 40 | N | 0
J-69 | 68 | LNG | 8 | 315 | 604 | O-69-4 | 317 | 화물창메공 | 4 | 476 | 519 | 43 | F | 26
J-69 | 68 | LNG | 8 | 315 | 604 | O-69-5 | 318 | 시운전 | 5 | 519 | 536 | 17 | N | 0
J-69 | 68 | LNG | 8 | 315 | 604 | O-69-6 | 319 | C/T | 6 | 536 | 553 | 17 | S | 7
J-69 | 68 | LNG | 8 | 315 | 604 | O-69-7 | 320 | G/T | 7 | 553 | 579 | 26 | N | 0
J-69 | 68 | LNG | 8 | 315 | 604 | O-69-8 | 321 | 인도준비 | 8 | 579 | 604 | 25 | S | 5
J-70 | 69 | LNG | 8 | 321 | 633 | O-70-1 | 322 | 화물창 | 1 | 321 | 423 | 102 | N | 0
J-70 | 69 | LNG | 8 | 321 | 633 | O-70-2 | 323 | P/T | 2 | 423 | 451 | 28 | F | 15
J-70 | 69 | LNG | 8 | 321 | 633 | O-70-3 | 324 | 화물창족철 | 3 | 451 | 494 | 43 | N | 0
J-70 | 69 | LNG | 8 | 321 | 633 | O-70-4 | 325 | 화물창메공 | 4 | 494 | 540 | 46 | F | 26
J-70 | 69 | LNG | 8 | 321 | 633 | O-70-5 | 326 | 시운전 | 5 | 540 | 558 | 18 | N | 0
J-70 | 69 | LNG | 8 | 321 | 633 | O-70-6 | 327 | C/T | 6 | 558 | 576 | 18 | S | 7
J-70 | 69 | LNG | 8 | 321 | 633 | O-70-7 | 328 | G/T | 7 | 576 | 604 | 28 | N | 0
J-70 | 69 | LNG | 8 | 321 | 633 | O-70-8 | 329 | 인도준비 | 8 | 604 | 633 | 29 | S | 5
J-71 | 70 | A_COT | 4 | 323 | 482 | O-71-1 | 330 | 축계작업 | 1 | 323 | 407 | 84 | F | 10
J-71 | 70 | A_COT | 4 | 323 | 482 | O-71-2 | 331 | 시운전 | 2 | 407 | 437 | 30 | N | 0
J-71 | 70 | A_COT | 4 | 323 | 482 | O-71-3 | 332 | 인도준비 | 3 | 437 | 482 | 45 | N | 0
J-72 | 71 | LNG | 8 | 324 | 517 | O-72-1 | 333 | 화물창 | 1 | 324 | 387 | 63 | N | 0
J-72 | 71 | LNG | 8 | 324 | 517 | O-72-2 | 334 | P/T | 2 | 387 | 404 | 17 | F | 15
J-72 | 71 | LNG | 8 | 324 | 517 | O-72-3 | 335 | 화물창족철 | 3 | 404 | 431 | 27 | N | 0
J-72 | 71 | LNG | 8 | 324 | 517 | O-72-4 | 336 | 화물창메공 | 4 | 431 | 459 | 28 | F | 26
J-72 | 71 | LNG | 8 | 324 | 517 | O-72-5 | 337 | 시운전 | 5 | 459 | 470 | 11 | N | 0
J-72 | 71 | LNG | 8 | 324 | 517 | O-72-6 | 338 | C/T | 6 | 470 | 481 | 11 | S | 7
J-72 | 71 | LNG | 8 | 324 | 517 | O-72-7 | 339 | G/T | 7 | 481 | 498 | 17 | N | 0
J-72 | 71 | LNG | 8 | 324 | 517 | O-72-8 | 340 | 인도준비 | 8 | 498 | 517 | 19 | S | 5
J-73 | 72 | A_COT | 4 | 328 | 403 | O-73-1 | 341 | 축계작업 | 1 | 328 | 367 | 39 | F | 10
J-73 | 72 | A_COT | 4 | 328 | 403 | O-73-2 | 342 | 시운전 | 2 | 367 | 381 | 14 | N | 0
J-73 | 72 | A_COT | 4 | 328 | 403 | O-73-3 | 343 | 인도준비 | 3 | 381 | 403 | 22 | N | 0
J-74 | 73 | S_COT | 3 | 335 | 460 | O-74-1 | 344 | 축계작업 | 1 | 335 | 401 | 66 | F | 10
J-74 | 73 | S_COT | 3 | 335 | 460 | O-74-2 | 345 | 시운전 | 2 | 401 | 424 | 23 | N | 0
J-74 | 73 | S_COT | 3 | 335 | 460 | O-74-3 | 346 | 인도준비 | 3 | 424 | 460 | 36 | N | 0
J-75 | 74 | PC | 7 | 335 | 470 | O-75-1 | 347 | 특수도장 | 1 | 335 | 379 | 44 | N | 0
J-75 | 74 | PC | 7 | 335 | 470 | O-75-2 | 348 | 화물창 | 2 | 379 | 424 | 45 | N | 0
J-75 | 74 | PC | 7 | 335 | 470 | O-75-3 | 349 | 시운전 | 3 | 424 | 438 | 14 | N | 0
J-75 | 74 | PC | 7 | 335 | 470 | O-75-4 | 350 | 인도준비 | 4 | 438 | 470 | 32 | S | 15
J-76 | 75 | VL_CONT | 6 | 335 | 443 | O-76-1 | 351 | 축계작업 | 1 | 335 | 410 | 75 | F | 15
J-76 | 75 | VL_CONT | 6 | 335 | 443 | O-76-2 | 352 | 시운전 | 2 | 410 | 420 | 10 | N | 0
J-76 | 75 | VL_CONT | 6 | 335 | 443 | O-76-3 | 353 | 인도준비 | 3 | 420 | 443 | 23 | N | 0
J-77 | 76 | A_SHTL | 2 | 340 | 536 | O-77-1 | 354 | 축계작업 | 1 | 340 | 485 | 145 | F | 15
J-77 | 76 | A_SHTL | 2 | 340 | 536 | O-77-2 | 355 | 시운전 | 2 | 485 | 506 | 21 | N | 0
J-77 | 76 | A_SHTL | 2 | 340 | 536 | O-77-3 | 356 | 인도준비 | 3 | 506 | 536 | 30 | N | 0
J-78 | 77 | VL_CONT | 6 | 345 | 445 | O-78-1 | 357 | 축계작업 | 1 | 345 | 415 | 70 | F | 15
J-78 | 77 | VL_CONT | 6 | 345 | 445 | O-78-2 | 358 | 시운전 | 2 | 415 | 425 | 10 | N | 0
J-78 | 77 | VL_CONT | 6 | 345 | 445 | O-78-3 | 359 | 인도준비 | 3 | 425 | 445 | 20 | N | 0
J-79 | 78 | LNG | 8 | 351 | 632 | O-79-1 | 360 | 화물창 | 1 | 351 | 443 | 92 | N | 0
J-79 | 78 | LNG | 8 | 351 | 632 | O-79-2 | 361 | P/T | 2 | 443 | 468 | 25 | F | 15
J-79 | 78 | LNG | 8 | 351 | 632 | O-79-3 | 362 | 화물창족철 | 3 | 468 | 507 | 39 | N | 0
J-79 | 78 | LNG | 8 | 351 | 632 | O-79-4 | 363 | 화물창메공 | 4 | 507 | 549 | 42 | F | 26
J-79 | 78 | LNG | 8 | 351 | 632 | O-79-5 | 364 | 시운전 | 5 | 549 | 565 | 16 | N | 0
J-79 | 78 | LNG | 8 | 351 | 632 | O-79-6 | 365 | C/T | 6 | 565 | 581 | 16 | S | 7
J-79 | 78 | LNG | 8 | 351 | 632 | O-79-7 | 366 | G/T | 7 | 581 | 606 | 25 | N | 0
J-79 | 78 | LNG | 8 | 351 | 632 | O-79-8 | 367 | 인도준비 | 8 | 606 | 632 | 26 | S | 5
J-80 | 79 | A_SHTL | 2 | 351 | 591 | O-80-1 | 368 | 축계작업 | 1 | 351 | 528 | 177 | F | 15
J-80 | 79 | A_SHTL | 2 | 351 | 591 | O-80-2 | 369 | 시운전 | 2 | 528 | 554 | 26 | N | 0
J-80 | 79 | A_SHTL | 2 | 351 | 591 | O-80-3 | 370 | 인도준비 | 3 | 554 | 591 | 37 | N | 0
J-81 | 80 | L_CONT | 5 | 357 | 427 | O-81-1 | 371 | 축계작업 | 1 | 357 | 406 | 49 | F | 15
J-81 | 80 | L_CONT | 5 | 357 | 427 | O-81-2 | 372 | 시운전 | 2 | 406 | 413 | 7 | N | 0
J-81 | 80 | L_CONT | 5 | 357 | 427 | O-81-3 | 373 | 인도준비 | 3 | 413 | 427 | 14 | N | 0
J-82 | 81 | S_SHTL | 1 | 357 | 525 | O-82-1 | 374 | 축계작업 | 1 | 357 | 481 | 124 | F | 15
J-82 | 81 | S_SHTL | 1 | 357 | 525 | O-82-2 | 375 | 시운전 | 2 | 481 | 499 | 18 | N | 0
J-82 | 81 | S_SHTL | 1 | 357 | 525 | O-82-3 | 376 | 인도준비 | 3 | 499 | 525 | 26 | N | 0
J-83 | 82 | LNG | 8 | 358 | 605 | O-83-1 | 377 | 화물창 | 1 | 358 | 439 | 81 | N | 0
J-83 | 82 | LNG | 8 | 358 | 605 | O-83-2 | 378 | P/T | 2 | 439 | 461 | 22 | F | 15
J-83 | 82 | LNG | 8 | 358 | 605 | O-83-3 | 379 | 화물창족철 | 3 | 461 | 495 | 34 | N | 0
J-83 | 82 | LNG | 8 | 358 | 605 | O-83-4 | 380 | 화물창메공 | 4 | 495 | 532 | 37 | F | 26
J-83 | 82 | LNG | 8 | 358 | 605 | O-83-5 | 381 | 시운전 | 5 | 532 | 546 | 14 | N | 0
J-83 | 82 | LNG | 8 | 358 | 605 | O-83-6 | 382 | C/T | 6 | 546 | 560 | 14 | S | 7
J-83 | 82 | LNG | 8 | 358 | 605 | O-83-7 | 383 | G/T | 7 | 560 | 582 | 22 | N | 0
J-83 | 82 | LNG | 8 | 358 | 605 | O-83-8 | 384 | 인도준비 | 8 | 582 | 605 | 23 | S | 5
J-84 | 83 | LNG | 8 | 358 | 583 | O-84-1 | 385 | 화물창 | 1 | 358 | 432 | 74 | N | 0
J-84 | 83 | LNG | 8 | 358 | 583 | O-84-2 | 386 | P/T | 2 | 432 | 452 | 20 | F | 15
J-84 | 83 | LNG | 8 | 358 | 583 | O-84-3 | 387 | 화물창족철 | 3 | 452 | 483 | 31 | N | 0
J-84 | 83 | LNG | 8 | 358 | 583 | O-84-4 | 388 | 화물창메공 | 4 | 483 | 516 | 33 | F | 26
J-84 | 83 | LNG | 8 | 358 | 583 | O-84-5 | 389 | 시운전 | 5 | 516 | 529 | 13 | N | 0
J-84 | 83 | LNG | 8 | 358 | 583 | O-84-6 | 390 | C/T | 6 | 529 | 542 | 13 | S | 7
J-84 | 83 | LNG | 8 | 358 | 583 | O-84-7 | 391 | G/T | 7 | 542 | 562 | 20 | N | 0
J-84 | 83 | LNG | 8 | 358 | 583 | O-84-8 | 392 | 인도준비 | 8 | 562 | 583 | 21 | S | 5
J-85 | 84 | LNG | 8 | 363 | 635 | O-85-1 | 393 | 화물창 | 1 | 363 | 452 | 89 | N | 0
J-85 | 84 | LNG | 8 | 363 | 635 | O-85-2 | 394 | P/T | 2 | 452 | 476 | 24 | F | 15
J-85 | 84 | LNG | 8 | 363 | 635 | O-85-3 | 395 | 화물창족철 | 3 | 476 | 514 | 38 | N | 0
J-85 | 84 | LNG | 8 | 363 | 635 | O-85-4 | 396 | 화물창메공 | 4 | 514 | 554 | 40 | F | 26
J-85 | 84 | LNG | 8 | 363 | 635 | O-85-5 | 397 | 시운전 | 5 | 554 | 570 | 16 | N | 0
J-85 | 84 | LNG | 8 | 363 | 635 | O-85-6 | 398 | C/T | 6 | 570 | 586 | 16 | S | 7
J-85 | 84 | LNG | 8 | 363 | 635 | O-85-7 | 399 | G/T | 7 | 586 | 610 | 24 | N | 0
J-85 | 84 | LNG | 8 | 363 | 635 | O-85-8 | 400 | 인도준비 | 8 | 610 | 635 | 25 | S | 5
J-86 | 85 | LNG | 8 | 367 | 650 | O-86-1 | 401 | 화물창 | 1 | 367 | 460 | 93 | N | 0
J-86 | 85 | LNG | 8 | 367 | 650 | O-86-2 | 402 | P/T | 2 | 460 | 485 | 25 | F | 15
J-86 | 85 | LNG | 8 | 367 | 650 | O-86-3 | 403 | 화물창족철 | 3 | 485 | 524 | 39 | N | 0
J-86 | 85 | LNG | 8 | 367 | 650 | O-86-4 | 404 | 화물창메공 | 4 | 524 | 566 | 42 | F | 26
J-86 | 85 | LNG | 8 | 367 | 650 | O-86-5 | 405 | 시운전 | 5 | 566 | 582 | 16 | N | 0
J-86 | 85 | LNG | 8 | 367 | 650 | O-86-6 | 406 | C/T | 6 | 582 | 598 | 16 | S | 7
J-86 | 85 | LNG | 8 | 367 | 650 | O-86-7 | 407 | G/T | 7 | 598 | 623 | 25 | N | 0
J-86 | 85 | LNG | 8 | 367 | 650 | O-86-8 | 408 | 인도준비 | 8 | 623 | 650 | 27 | S | 5
J-87 | 86 | A_SHTL | 2 | 368 | 619 | O-87-1 | 409 | 축계작업 | 1 | 368 | 553 | 185 | F | 15
J-87 | 86 | A_SHTL | 2 | 368 | 619 | O-87-2 | 410 | 시운전 | 2 | 553 | 580 | 27 | N | 0
J-87 | 86 | A_SHTL | 2 | 368 | 619 | O-87-3 | 411 | 인도준비 | 3 | 580 | 619 | 39 | N | 0
J-88 | 87 | A_COT | 4 | 368 | 472 | O-88-1 | 412 | 축계작업 | 1 | 368 | 423 | 55 | F | 10
J-88 | 87 | A_COT | 4 | 368 | 472 | O-88-2 | 413 | 시운전 | 2 | 423 | 442 | 19 | N | 0
J-88 | 87 | A_COT | 4 | 368 | 472 | O-88-3 | 414 | 인도준비 | 3 | 442 | 472 | 30 | N | 0
J-89 | 88 | L_CONT | 5 | 376 | 452 | O-89-1 | 415 | 축계작업 | 1 | 376 | 429 | 53 | F | 15
J-89 | 88 | L_CONT | 5 | 376 | 452 | O-89-2 | 416 | 시운전 | 2 | 429 | 436 | 7 | N | 0
J-89 | 88 | L_CONT | 5 | 376 | 452 | O-89-3 | 417 | 인도준비 | 3 | 436 | 452 | 16 | N | 0
J-90 | 89 | VL_CONT | 6 | 381 | 512 | O-90-1 | 418 | 축계작업 | 1 | 381 | 472 | 91 | F | 15
J-90 | 89 | VL_CONT | 6 | 381 | 512 | O-90-2 | 419 | 시운전 | 2 | 472 | 485 | 13 | N | 0
J-90 | 89 | VL_CONT | 6 | 381 | 512 | O-90-3 | 420 | 인도준비 | 3 | 485 | 512 | 27 | N | 0
J-91 | 90 | A_SHTL | 2 | 386 | 594 | O-91-1 | 421 | 축계작업 | 1 | 386 | 539 | 153 | F | 15
J-91 | 90 | A_SHTL | 2 | 386 | 594 | O-91-2 | 422 | 시운전 | 2 | 539 | 561 | 22 | N | 0
J-91 | 90 | A_SHTL | 2 | 386 | 594 | O-91-3 | 423 | 인도준비 | 3 | 561 | 594 | 33 | N | 0
J-92 | 91 | VL_CONT | 6 | 386 | 520 | O-92-1 | 424 | 축계작업 | 1 | 386 | 479 | 93 | F | 15
J-92 | 91 | VL_CONT | 6 | 386 | 520 | O-92-2 | 425 | 시운전 | 2 | 479 | 492 | 13 | N | 0
J-92 | 91 | VL_CONT | 6 | 386 | 520 | O-92-3 | 426 | 인도준비 | 3 | 492 | 520 | 28 | N | 0
J-93 | 92 | A_SHTL | 2 | 386 | 630 | O-93-1 | 427 | 축계작업 | 1 | 386 | 566 | 180 | F | 15
J-93 | 92 | A_SHTL | 2 | 386 | 630 | O-93-2 | 428 | 시운전 | 2 | 566 | 592 | 26 | N | 0
J-93 | 92 | A_SHTL | 2 | 386 | 630 | O-93-3 | 429 | 인도준비 | 3 | 592 | 630 | 38 | N | 0
J-94 | 93 | S_COT | 3 | 389 | 493 | O-94-1 | 430 | 축계작업 | 1 | 389 | 444 | 55 | F | 10
J-94 | 93 | S_COT | 3 | 389 | 493 | O-94-2 | 431 | 시운전 | 2 | 444 | 463 | 19 | N | 0
J-94 | 93 | S_COT | 3 | 389 | 493 | O-94-3 | 432 | 인도준비 | 3 | 463 | 493 | 30 | N | 0
J-95 | 94 | LNG | 8 | 390 | 594 | O-95-1 | 433 | 화물창 | 1 | 390 | 457 | 67 | N | 0
J-95 | 94 | LNG | 8 | 390 | 594 | O-95-2 | 434 | P/T | 2 | 457 | 475 | 18 | F | 15
J-95 | 94 | LNG | 8 | 390 | 594 | O-95-3 | 435 | 화물창족철 | 3 | 475 | 503 | 28 | N | 0
J-95 | 94 | LNG | 8 | 390 | 594 | O-95-4 | 436 | 화물창메공 | 4 | 503 | 533 | 30 | F | 26
J-95 | 94 | LNG | 8 | 390 | 594 | O-95-5 | 437 | 시운전 | 5 | 533 | 545 | 12 | N | 0
J-95 | 94 | LNG | 8 | 390 | 594 | O-95-6 | 438 | C/T | 6 | 545 | 557 | 12 | S | 7
J-95 | 94 | LNG | 8 | 390 | 594 | O-95-7 | 439 | G/T | 7 | 557 | 575 | 18 | N | 0
J-95 | 94 | LNG | 8 | 390 | 594 | O-95-8 | 440 | 인도준비 | 8 | 575 | 594 | 19 | S | 5
J-96 | 95 | VL_CONT | 6 | 391 | 493 | O-96-1 | 441 | 축계작업 | 1 | 391 | 462 | 71 | F | 15
J-96 | 95 | VL_CONT | 6 | 391 | 493 | O-96-2 | 442 | 시운전 | 2 | 462 | 472 | 10 | N | 0
J-96 | 95 | VL_CONT | 6 | 391 | 493 | O-96-3 | 443 | 인도준비 | 3 | 472 | 493 | 21 | N | 0
J-97 | 96 | A_COT | 4 | 397 | 556 | O-97-1 | 444 | 축계작업 | 1 | 397 | 481 | 84 | F | 10
J-97 | 96 | A_COT | 4 | 397 | 556 | O-97-2 | 445 | 시운전 | 2 | 481 | 511 | 30 | N | 0
J-97 | 96 | A_COT | 4 | 397 | 556 | O-97-3 | 446 | 인도준비 | 3 | 511 | 556 | 45 | N | 0
J-98 | 97 | PC | 7 | 397 | 516 | O-98-1 | 447 | 특수도장 | 1 | 397 | 436 | 39 | N | 0
J-98 | 97 | PC | 7 | 397 | 516 | O-98-2 | 448 | 화물창 | 2 | 436 | 476 | 40 | N | 0
J-98 | 97 | PC | 7 | 397 | 516 | O-98-3 | 449 | 시운전 | 3 | 476 | 489 | 13 | N | 0
J-98 | 97 | PC | 7 | 397 | 516 | O-98-4 | 450 | 인도준비 | 4 | 489 | 516 | 27 | S | 15
J-99 | 98 | L_CONT | 5 | 410 | 489 | O-99-1 | 451 | 축계작업 | 1 | 410 | 465 | 55 | F | 15
J-99 | 98 | L_CONT | 5 | 410 | 489 | O-99-2 | 452 | 시운전 | 2 | 465 | 472 | 7 | N | 0
J-99 | 98 | L_CONT | 5 | 410 | 489 | O-99-3 | 453 | 인도준비 | 3 | 472 | 489 | 17 | N | 0
J-100 | 99 | S_COT | 3 | 420 | 534 | O-100-1 | 454 | 축계작업 | 1 | 420 | 480 | 60 | F | 10
J-100 | 99 | S_COT | 3 | 420 | 534 | O-100-2 | 455 | 시운전 | 2 | 480 | 501 | 21 | N | 0
J-100 | 99 | S_COT | 3 | 420 | 534 | O-100-3 | 456 | 인도준비 | 3 | 501 | 534 | 33 | N | 0

## initial
Ship_Name | Ship_Index | Ship_Type | Category | Launching_Date | Delivery_Date | Operation_Name | Operation_Index | Operation_Type | Order | Start_Date | Finish_Date | Duration | Interruption | Fixed_Duration | Quay_Assigned
J-1 | 0 | LNG | 8 | 0 | 231 | O-1-1 | 0 | 화물창 | 1 | 0 | 76 | 76 | N | 0 | H1
J-2 | 1 | PC | 7 | 0 | 118 | O-2-1 | 8 | 특수도장 | 1 | 0 | 38 | 38 | N | 0 | D3
J-3 | 2 | VL_CONT | 6 | 2 | 133 | O-3-1 | 12 | 축계작업 | 1 | 2 | 93 | 91 | F | 15 | E8
J-4 | 3 | LNG | 8 | 2 | 223 | O-4-1 | 15 | 화물창 | 1 | 2 | 74 | 72 | N | 0 | X12
J-5 | 4 | VL_CONT | 6 | 5 | 145 | O-5-1 | 23 | 축계작업 | 1 | 5 | 103 | 98 | F | 15 | E5

## quay
선종 | 작업 | A1 | A2 | A3 | A4 | B1 | B2 | B3 | C1 | C2 | C3 | C4 | D1 | D2 | D3 | D4 | D5 | F1 | G1 | H1 | H2 | E1 | E2 | E3 | E4 | E5 | E6 | E7 | E8 | X1 | X2 | X3 | X4 | X5 | X6 | X7 | X8 | X9 | X10 | X11 | X12
LNG | 화물창 | B | A | A | A | B | A | A | A | A | A | A | A | A | A | N | B | N | A | B | B | D | D | D | D | D | D | D | D | N | B | A | A | A | B | A | A | A | A | B | B
LNG | P/T | E | E | E | A | E | A | A | E | E | E | E | E | E | E | N | E | N | A | E | E | E | E | E | E | E | E | E | E | N | E | E | E | A | E | A | A | E | A | E | E
LNG | 화물창족철 | E | A | A | A | E | A | A | B | B | B | B | B | B | B | N | B | N | A | C | C | D | D | D | D | D | D | D | D | N | E | A | A | A | E | A | A | B | A | C | C
LNG | 화물창메공 | C | A | A | A | A | A | A | A | A | A | A | A | A | A | N | A | N | A | C | C | E | E | E | E | E | E | E | E | N | C | A | A | A | A | A | A | A | A | C | C
LNG | 시운전 | bar: E C to C C
LNG | C/T | A | A | A | E | E | E | E | E | E | E | E | E | E | E | N | E | N | E | E | E | E | E | E | E | E | E | E | E | N | A | A | A | E | E | E | E | E | E | E | E
LNG | G/T | bar: E C to C C
LNG | 인도준비 | B | A | A | A | B | A | A | A | A | A | A | A | A | A | A | A | N | A | B | B | D | D | D | D | D | D | D | D | N | B | A | A | A | B | A | A | A | A | B | B
VL_CONT | 축계작업 | N | N | N | N | N | N | N | N | N | A | A | N | A | A | A | A | N | N | N | N | N | N | D | D | D | D | D | D | N | N | N | N | N | N | N | N | N | N | N | N
VL_CONT | 시운전 | bar: B to B
VL_CONT | 인도준비 | N | N | N | N | N | N | N | N | N | A | A | N | A | A | A | A | N | N | N | N | N | N | D | D | D | D | D | D | N | N | N | N | N | N | N | N | N | N | N | N
L_CONT | 축계작업 | N | N | N | N | N | N | N | D | D | A | A | N | A | A | A | A | N | N | N | N | N | N | D | D | D | D | D | D | N | N | N | N | N | N | N | N | N | N | N | N
L_CONT | 시운전 | bar: B to B
L_CONT | 인도준비 | N | N | N | N | N | N | N | D | D | A | A | N | A | A | A | A | N | N | N | N | N | N | D | D | D | D | D | D | N | N | N | N | N | N | N | N | N | N | N | N
M_CONT | 축계작업 | N | N | N | N | N | N | N | C | C | A | A | N | A | A | A | A | N | A | N | N | N | N | D | D | D | D | D | D | N | N | N | N | N | N | N | N | N | A | N | N
M_CONT | 시운전 | bar: N to N
M_CONT | 인도준비 | N | N | N | N | N | N | N | C | C | A | A | N | A | A | A | A | N | A | N | N | N | N | D | D | D | D | D | D | N | N | N | N | N | N | N | N | N | A | N | N
DRILL | 본선작업1 | bar: N to N
DRILL | A/T | N | N | N | N | N | N | N | E | N | A | A | N | B | B | A | A | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
DRILL | 본선작업2 | N | N | N | N | N | N | N | B | N | A | A | N | B | A | A | A | N | N | N | N | C | C | C | C | C | C | C | C | N | N | N | N | N | N | N | N | N | N | N | N
DRILL | 시운전 | bar: N N to N N
DRILL | 본선작업3 | N | N | N | N | N | N | N | B | N | A | A | N | B | A | A | A | N | N | N | N | C | C | C | C | C | C | C | C | N | N | N | N | N | N | N | N | N | N | N | N
DRILL | D/P시운전 | bar: N to N
DRILL | 인도준비 | N | N | N | N | N | N | N | B | N | A | A | N | B | A | A | A | N | N | N | N | C | C | C | C | C | C | C | C | N | N | N | N | N | N | N | N | N | N | N | N
PC | 특수도장 | bar: N to N
PC | 화물창 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | B | B | B | B | B | B | B | B | A | A | A | A | A | A | A | A | A | A | A | A
PC | 시운전 | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
PC | 인도준비 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | B | B | C | C | C | C | C | C | C | C | A | A | A | A | A | A | A | A | A | A | B | B
VLCC | 축계작업 | N | N | N | N | N | N | N | A | A | A | A | B | A | A | A | A | N | A | C | C | D | D | D | D | D | D | D | D | N | N | N | N | N | N | N | N | B | A | C | C
VLCC | 시운전 | bar: N to C
VLCC | 인도준비 | N | N | N | N | N | N | N | A | A | A | A | B | A | A | A | A | N | A | C | C | D | D | D | D | D | D | D | D | N | N | N | N | N | N | N | N | B | A | C | C
S_SHTL | 축계작업 | B | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | N | A | A | A | C | C | B | B | B | B | B | B | N | B | A | A | A | A | A | A | A | A | A | A
S_SHTL | 시운전 | bar: N B to C A
S_SHTL | 인도준비 | B | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | N | A | A | A | C | C | B | B | B | B | B | B | N | B | A | A | A | A | A | A | A | A | A | A
A_SHTL | 축계작업 | B | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | C | C | B | B | B | B | B | B | A | B | A | A | A | A | A | A | A | A | A | A
A_SHTL | 시운전 | bar: B to A
A_SHTL | 인도준비 | B | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | C | C | B | B | B | B | B | B | A | B | A | A | A | A | A | A | A | A | A | A
S_COT | 축계작업 | B | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | N | A | A | A | C | C | B | B | B | B | B | B | N | B | A | A | A | A | A | A | A | A | A | A
S_COT | 시운전 | bar: B to A
S_COT | 인도준비 | B | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | N | A | A | A | C | C | B | B | B | B | B | B | N | B | A | A | A | A | A | A | A | A | A | A
A_COT | 축계작업 | B | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | C | C | B | B | B | B | B | B | A | B | A | A | A | A | A | A | A | A | A | A
A_COT | 시운전 | bar: B to A
A_COT | 인도준비 | B | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | C | C | B | B | B | B | B | B | A | B | A | A | A | A | A | A | A | A | A | A